## Slide 1
AI-Powered Smart Routing & Instant Retry - Enhancing Nimbus Pay's Payment Orchestration
Builds on company's Smart Transaction Router (STR), not a rebuild
Adds real-time ML success-probability scoring + compliance-aware instant retry on top of the current rule-based Smart Transaction Router
Delivered as a phased pilot → compliance validation → scaled rollout
Executive Summary:
PhorSense

## Slide 2
Payment Lifecycle & Ecosystem Map
Supported channels: Cards • UPI • Aadhaar • Wallets • NEFT/RTGS • eNACH — across Online, In-Store, and Doorstep channels
➝
➝
➝
Retry Decision
Routing decision
Customer
Merchant
Checkout
Card Network
/ NPCI
➝
Issuing
Bank
Phor
Orchestration
➝
Acquirer /
PA / PG
Both decisions are made at the Phor orchestration layer:
Routing - which gateway/acquirer to use before sending
Retry - evaluated once a decline signal returns from the issuer through the network and acquirer

## Slide 3
AI Application & Value Proposition
80-85%
Typical single-gateway
success rate baseline
62%
Of customers never return
after a failed transaction
95%
Industry benchmark for
strong performance
5-10%
Company's own claimed range: Smart Router 5%+, Phor (insurance) up to 10%
Why AI over static rules:
Rule-based routing (Phor today) is static. An ML model scores each route's real-time success probability using card BIN, issuing bank, amount, and time of day, adapting as issuer behavior shifts, instead of needing manual retuning.
The retry differentiator:
Soft declines (network issue, timeout) are retriable while hard declines (stolen/closed card) are not. Retrying hard declines wastes resources and can trigger Visa/Mastercard excessive-retry penalty programs. Retry logic must classify by decline category, not raw code.

## Slide 4
Work Breakdown Structure (WBS)
02 | Data Foundation
Historical transaction data pipeline build
Decline-reason taxonomy
PCI-scoped tokenization & data quality checks
ML feature store setup
01 | Discovery
Scope & stakeholder interviews
Current-state routing-rule & decline-data audit
Success criteria, KPI targets & scope sign-off
04 | Model Development
Feature engineering - routing success-probability model
Train & validate routing success-probability model.
Feature engineering - risk/fraud scoring model
Train & validate risk scoring model
Model review
03 | Compliance Review
PCI DSS v4.0.1 scoped impact assessment
RBI Payment Aggregator Master Direction & Cyber Resilience alignment review
CERT-In audit readiness check
06 | Testing
Shadow-mode parallel-run infrastructure setup
Shadow-mode observation
A-B ramp vs. current rule-based router
Test report & success-rate delta analysis
05 | Engine Build
Smart Routing service
Smart Retry service
Risk Engine integration
Phor / Smart Transaction Router API integration layer
Idempotency key handling & reconciliation logic
Code review, unit & integration testing
08 | Scaled Rollout
Phased onboarding
Live success-rate dashboard build & handover
SOP handbook finalization & Scrum team training
Retraining cadence & drift-monitoring alerts setup
07 | Pilot Rollout
Pilot merchant selection & SLA terms agreement
Limited live-traffic cutover (one merchant segment)
Pilot monitoring & escalation SOP live
Pilot results review & go/no-go decision

## Slide 5
Project Plan & Deliverables
Phase | Milestones | Deliverables
Discovery | Scope & audit complete | Requirements doc, current-state audit
Data + Model | Model trained | Feature pipeline, model v1
Compliance Review | PCI/RBI/CERT-In sign-off complete | Compliance sign-off doc, audit trail
Engine Build | Services integrated | Routing + retry live in shadow mode
Shadow testing | Validated vs. baseline | Test reports, success-rate delta
Pilot | Limited live traffic | Pilot results, go/no-go decision
Scaled Rollout | Broader onboarding | SOP handbook, live dashboard

## Slide 6
Cross-Functional Dependency Matrix
Depends on:
Model artifacts (Data Science) API specs (Product)
Engineering
Delivers:
Routing/retry engine, integration endpoints
Depends on:
Merchant priorities from Sales/Ops
Product
Delivers:
Business rules (cost vs. success-rate trade-offs), roadmap
Depends on:
Decline taxonomy inputs during Discovery. Model outputs during
ongoing fraud-rule tuning
Risk & compliance
Delivers:
Fraud thresholds, decline taxonomy, compliance sign-off
Depends on:
Pilot merchant selection, SLA terms
Merchant / ops
Delivers:
Onboarding feedback, real-world performance data
Depends on:
Historical transaction data (Engineering), decline taxonomy (Risk & Compliance)
Data Science
Delivers:
Success-probability model, risk-scoring model, retraining pipeline

## Slide 7
Risk Management & Compliance Checkpoints
Regulatory (RBI)
Risk: RBI Payment Aggregator Master Direction + Cyber Resilience Directions
Fix: Compliance review built into WBS. CERT-In audit alignment
PCI DSS
Risk: v4.0.1 is the only active standard in 2026, enforceable since Mar 31, 2025
Fix: Continuous documented evidence, not annual-only checks
Card Network Penalties
Risk: Retrying against issuer “do not retry” signals triggers Visa/Mastercard penalty programs
Fix: Strict soft/hard decline classification, retry caps aligned to network rules
Model Drift
Risk: Model degrades as fraud/issuer patterns shift over time
Fix: Scheduled retraining, drift-monitoring alerts
Cold - Start
Risk: Model underperforms without sufficient historical data
Fix: Shadow-mode testing before any live traffic shift
Data Privacy
Risk: ML feature pipeline touches card-related data
Fix: PCI DSS-scoped handling, tokenization, no raw PAN in features

## Slide 8
Operational Readiness & SOP Handbook Framework
1) Escalation SOP
Action when a gateway's real-time success rate drops below threshold - auto-reroute + alert Ops
2) Manual Override SOP
How Ops pauses or overrides the ML router if something looks wrong
3) Merchant Communication SOP
How pilot merchants are informed of routing changes and expected impact
4) Monitoring Ownership
Who watches the live success-rate dashboard and the escalation chain
5) Rollback Plan
Criteria for reverting to the current rule-based router if the pilot underperforms

## Slide 9
KPI & Success Matrix
↓
False decline rate
(post-rollout target: decrease)
Retry recovery rate (soft declines only)
Directional target measured against the pilot baseline
5-10%
Target uplift range
(Phi Commerce's own Smart Router / Phor precedent)
95%+
Success-rate benchmark
(baseline 80–85%)
Routing decision latency
Must stay imperceptible to checkout UX
Revenue recovered
Tracked directly against pilot merchant's baseline decline-related loss

## Slide 10
Conclusion and Q&A
This isn't a new capability for NimbusPay - it's the natural next step:
Layering a self-optimizing success-probability model and a compliance-aware retry engine on top of the routing infrastructure that already exists.
Thank you